## Backend Backlog
ID | Nama Fitur | Kategori | Status | Prioritas | Deskripsi | Controller | Service | Model | API Endpoints | Database | Fitur Utama | Testing Status
BE-001 | Unified Authentication System | Authentication & Security | Completed | High | Sistem autentikasi terpadu dengan JWT + Sanctum + Refresh Token. Mendukung login, register, token refresh, password reset, dan session management. | AuthController.php | AuthService.php | User.php, UserSession.php | 16 auth endpoints lengkap | users, user_sessions, refresh_tokens, personal_access_tokens | JWT + Sanctum + Refresh token, rate limiting, session management, password reset | Production Ready
BE-002 | User Management System | User Management | Completed | High | Sistem manajemen user lengkap dengan CRUD operations, search, filtering, pagination, role assignment, dan profile management. | UserController.php | UserService.php | User.php | /api/v1/users dengan semua CRUD operations | users table dengan semua fields | User CRUD, search, filtering, pagination, role assignment, profile management | Production Ready
BE-003 | Role Management System | User Management | Completed | High | Sistem manajemen role lengkap dengan CRUD operations, role assignment, permission management, dan role statistics. | RoleManagementController.php | RoleService.php | Role.php, UserRole.php, RolePermission.php | /api/v1/roles dengan semua CRUD operations | roles, user_roles, role_permissions tables | Role CRUD, assignment, permission management, statistics, cloning | Production Ready
BE-004 | Permission Management System | User Management | Completed | High | Sistem manajemen permission lengkap dengan CRUD operations, permission groups, role assignment, dan user permission checking. | PermissionManagementController.php | PermissionService.php | Permission.php, PermissionGroup.php, PermissionGroupPermission.php | /api/v1/permissions dengan semua CRUD operations | permissions, permission_groups, permission_group_permissions tables | Permission CRUD, groups, role assignment, user checking, wildcard permissions | Production Ready
BE-005 | Organization Management System | Organization Management | Completed | High | Sistem manajemen organisasi lengkap dengan CRUD operations, user management, subscription management, dan organization statistics. | OrganizationController.php | OrganizationService.php | Organization.php | /api/v1/organizations dengan semua CRUD operations | organizations table dengan semua fields | Organization CRUD, user management, subscription, statistics, filtering | Production Ready
BE-006 | Subscription Plan Management | Billing & Subscription | Completed | High | Sistem manajemen subscription plan lengkap dengan CRUD operations, tier management, popular plans, dan plan statistics. | SubscriptionPlanController.php | SubscriptionPlanService.php | SubscriptionPlan.php, Subscription.php | /api/v1/subscription-plans dengan semua CRUD operations | subscription_plans, subscriptions tables | Plan CRUD, tier management, popular plans, statistics, sorting | Production Ready
BE-007 | Payment Transaction Management | Billing & Subscription | Completed | Medium | Sistem manajemen payment transaction untuk SuperAdmin dengan filtering, statistics, export, dan transaction history. | PaymentTransactionController.php | PaymentTransactionService.php | PaymentTransaction.php | /api/v1/payment-transactions dengan filtering dan export | payment_transactions table | Transaction listing, filtering, statistics, export, history tracking | Production Ready
BE-008 | Knowledge Base Management | Content Management | Completed | Medium | Sistem manajemen knowledge base dengan CRUD operations, search, categorization, tagging, dan approval workflow. | KnowledgeBaseController.php | KnowledgeBaseService.php | KnowledgeBaseItem.php, KnowledgeBaseCategory.php, KnowledgeBaseTag.php, KnowledgeBaseItemTag.php, KnowledgeBaseItemRelationship.php | /api/v1/knowledge-base dengan semua CRUD operations | knowledge_base_items, knowledge_base_categories, knowledge_base_tags, knowledge_base_item_tags, knowledge_base_item_relationships tables | Knowledge CRUD, search, categorization, tagging, relationships, approval workflow | Production Ready
BE-009 | Bot Personality Management | Bot Management | Completed | Medium | Sistem manajemen bot personality untuk organization admin dengan CRUD operations dan personality configuration. | BotPersonalityController.php | BotPersonalityService.php | BotPersonality.php | /api/v1/bot-personalities dengan CRUD operations | bot_personalities table | Personality CRUD, configuration, organization scoped, AI settings | Production Ready
BE-010 | Admin Dashboard & System Management | Administration | Completed | High | Dashboard admin dengan system overview, logs, health check, performance metrics, system maintenance, dan configuration management. | Admin routes dengan inline controllers | System services | SystemLog.php, AuditLog.php, RealtimeMetric.php | /api/admin/dashboard, /api/admin/analytics, /api/admin/maintenance | system_logs, audit_logs, realtime_metrics tables | System overview, logs, health check, performance, maintenance, configuration | Production Ready
BE-011 | Database Schema & Migrations | Infrastructure | Completed | High | Database schema lengkap dengan 50+ migrations untuk semua fitur sistem, termasuk indexes, foreign keys, dan constraints. | N/A | N/A | All models (50+ models) | N/A | 50+ tables dengan complete schema | Complete database schema, migrations, indexes, foreign keys, constraints | Production Ready
BE-012 | Middleware & Security System | Security | Completed | High | Sistem middleware dan security lengkap dengan unified auth, permission middleware, organization access, dan rate limiting. | N/A | N/A | N/A | N/A | N/A | Unified auth middleware, permission middleware, organization access, rate limiting, JWT + Sanctum | Production Ready
BE-013 | WAHA Integration System | Integration & Communication | Ongoing | High | Sistem integrasi WAHA (WhatsApp HTTP API) dengan session management, contact management, message handling, dan webhook processing. | Belum ada WAHA controller | Belum ada WAHA service | WahaSession.php, WahaContact.php, WahaGroup.php, WahaMessage.php, WahaWebhookEvent.php, WahaApiRequest.php, WahaRateLimit.php | WAHA endpoints belum diimplementasikan | waha_sessions, waha_contacts, waha_groups, waha_messages, waha_webhook_events, waha_api_requests, waha_rate_limits tables | Session management, contact sync, message handling, webhook processing, rate limiting | Models ready, API endpoints needed
BE-014 | Chat Session & Message Management | Communication Management | Ongoing | High | Sistem manajemen chat session dan message dengan real-time messaging, message history, dan conversation tracking. | Belum ada ChatController | Belum ada ChatService | ChatSession.php, Message.php, Customer.php, Agent.php | Chat endpoints belum diimplementasikan | chat_sessions, messages, customers, agents tables | Real-time messaging, message history, conversation tracking, customer management, agent management | Models ready, API endpoints needed
BE-015 | AI Model & Training System | AI & Machine Learning | Ongoing | Medium | Sistem AI model dan training dengan model management, training data collection, conversation logging, dan model optimization. | Belum ada AIController | Belum ada AIService | AiModel.php, AiTrainingData.php, AiConversationLog.php | AI endpoints belum diimplementasikan | ai_models, ai_training_data, ai_conversations_log tables | Model management, training data collection, conversation logging, model optimization | Models ready, API endpoints needed
BE-016 | N8n Workflow Integration | Automation | Ongoing | Medium | Sistem integrasi N8n workflow dengan workflow management, execution tracking, dan automation triggers. | N8nController.php (partial) | N8nService.php (partial) | N8nWorkflow.php, N8nExecution.php | N8n endpoints partial | n8n_workflows, n8n_executions tables | Workflow management, execution tracking, automation triggers, webhook integration | Partial implementation, needs completion
BE-017 | Analytics & Reporting System | Analytics & Reporting | Ongoing | Medium | Sistem analytics dan reporting dengan daily metrics, usage tracking, performance analytics, dan custom reports. | Belum ada AnalyticsController | Belum ada AnalyticsService | AnalyticsDaily.php, UsageTracking.php, RealtimeMetric.php | Analytics endpoints belum diimplementasikan | analytics_daily, usage_tracking, realtime_metrics tables | Daily metrics, usage tracking, performance analytics, custom reports, real-time metrics | Models ready, API endpoints needed
BE-018 | Webhook & Integration System | Integration | Ongoing | Medium | Sistem webhook dan integration dengan webhook management, delivery tracking, dan external API integration. | Belum ada WebhookController | Belum ada WebhookService | Webhook.php, WebhookDelivery.php | Webhook endpoints belum diimplementasikan | webhooks, webhook_deliveries tables | Webhook management, delivery tracking, external API integration, retry logic | Models ready, API endpoints needed
BE-019 | Chatbot Management System | Bot Management | Not Started | High | Sistem manajemen chatbot lengkap dengan CRUD operations, training, configuration, dan performance monitoring. | Belum ada ChatbotController | Belum ada ChatbotService | Belum ada Chatbot model | Chatbot endpoints belum ada | Chatbot tables belum ada | Chatbot CRUD, training, configuration, performance monitoring, AI integration | Not started
BE-020 | Real-time Notification System | Communication | Not Started | Medium | Sistem notifikasi real-time dengan WebSocket integration, push notifications, dan notification preferences. | Belum ada NotificationController | Belum ada NotificationService | Belum ada Notification model | Notification endpoints belum ada | Notification tables belum ada | WebSocket integration, push notifications, notification preferences, real-time updates | Not started
BE-021 | Advanced Security Features | Security | Not Started | High | Fitur keamanan advanced termasuk 2FA, audit logging, security compliance, dan threat detection. | Belum ada SecurityController | Belum ada SecurityService | Belum ada Security models | Security endpoints belum ada | Security tables belum ada | Two-factor authentication, audit logging, compliance reporting, threat detection | Not started
BE-022 | File Upload & Media Management | Content Management | Not Started | Medium | Sistem file upload dan media management dengan file storage, image processing, dan media optimization. | Belum ada MediaController | Belum ada MediaService | Belum ada Media model | Media endpoints belum ada | Media tables belum ada | File upload, image processing, media optimization, storage management | Not started
BE-023 | Email & Communication System | Communication | Not Started | Medium | Sistem email dan communication dengan email templates, sending, tracking, dan communication history. | Belum ada EmailController | Belum ada EmailService | Belum ada Email models | Email endpoints belum ada | Email tables belum ada | Email templates, sending, tracking, communication history, templates management | Not started
BE-024 | Advanced Analytics & BI | Analytics & Reporting | Not Started | Low | Sistem analytics dan business intelligence advanced dengan predictive analytics, custom dashboards, dan data visualization. | Belum ada BIController | Belum ada BIService | Belum ada BI models | BI endpoints belum ada | BI tables belum ada | Predictive analytics, custom dashboards, data visualization, business intelligence | Not started