## Frontend Backlog Enhanced
ID | Nama Fitur | Kategori | Status | Prioritas | Deskripsi | API Endpoints | Status API Backend
FEAT-001 | Unified Authentication System | Authentication & Security | Completed | High | Implementasi sistem autentikasi terpadu dengan JWT + Sanctum + Refresh Token strategy. Mendukung login dengan username/email, token management otomatis, dan fallback mechanism. | 16 auth endpoints lengkap | ✅ COMPLETED
FEAT-002 | Role Management System | User Management | Completed | High | Sistem manajemen role lengkap dengan CRUD operations, bulk operations, user assignment, permission management, dan analytics dashboard. | /api/v1/roles dengan semua CRUD operations | ✅ COMPLETED
FEAT-003 | User Management System | User Management | Completed | High | Sistem manajemen user lengkap dengan CRUD operations, search, statistics, activity tracking, dan permission management. | /api/v1/users dengan semua CRUD operations | ✅ COMPLETED
FEAT-004 | Permission Management System | User Management | Completed | High | Sistem manajemen permission lengkap dengan CRUD operations, permission groups, role assignment, dan user permission checking. | /api/v1/permissions dengan semua CRUD operations | ✅ COMPLETED
FEAT-005 | Organization Management System | Organization Management | Completed | High | Sistem manajemen organisasi lengkap dengan CRUD operations, user management, subscription management, dan statistics. | /api/v1/organizations dengan semua CRUD operations | ✅ COMPLETED
FEAT-006 | Subscription Plan Management | Billing & Subscription | Completed | High | Sistem manajemen subscription plan lengkap dengan CRUD operations, tier management, popular plans, dan statistics. | /api/v1/subscription-plans dengan semua CRUD operations | ✅ COMPLETED
FEAT-007 | Payment Transaction Management | Billing & Subscription | Completed | High | Sistem manajemen payment transaction untuk SuperAdmin dengan filtering, statistics, export, dan history tracking. | /api/v1/payment-transactions dengan filtering dan export | ✅ COMPLETED
FEAT-008 | Knowledge Base Management | Content Management | Ongoing | High | Sistem manajemen knowledge base dengan CRUD operations, search, categorization, publishing workflow, dan approval system. | /api/v1/knowledge-base dengan semua CRUD operations | ✅ COMPLETED
FEAT-009 | Bot Personality Management | Bot Management | Ongoing | High | Sistem manajemen bot personality untuk organization admin dengan CRUD operations dan personality configuration. | /api/v1/bot-personalities dengan CRUD operations | ✅ COMPLETED
FEAT-010 | Admin Dashboard & Analytics | Administration | Ongoing | High | Dashboard admin dengan system overview, logs, health check, performance metrics, dan system maintenance. | /api/admin/dashboard, /api/admin/analytics | ✅ COMPLETED
FEAT-011 | Agent Dashboard & Interface | Agent Management | Ongoing | High | Dashboard agent profesional dengan metrics real-time, 3-panel chat interface, performance tracking, dan leaderboard system. | Agent-specific endpoints (partial) | 🔄 PARTIAL - Frontend ready, API endpoints belum lengkap
FEAT-012 | WhatsApp QR Integration | Integration & Communication | Ongoing | High | Integrasi WhatsApp via QR Code dengan WAHA session. Step-by-step wizard interface dengan timeout management dan error handling. | WAHA session management endpoints (partial) | 🔄 PARTIAL - Frontend ready, WAHA integration belum lengkap
FEAT-013 | Inbox Management System | Communication Management | Ongoing | High | Sistem manajemen inbox lengkap dengan platform management, statistics dashboard, dan multi-channel support. | Inbox dan session management endpoints (partial) | 🔄 PARTIAL - Frontend ready, inbox API belum lengkap
FEAT-014 | Client Management Features | Client Management | Ongoing | Medium | Fitur manajemen client dengan billing, communication, notes, success plays, users, dan workflows management. | Client management endpoints (partial) | 🔄 PARTIAL - Frontend ready, client API belum lengkap
FEAT-015 | SuperAdmin Dashboard | Administration | Ongoing | High | Dashboard SuperAdmin dengan client management, financials, onboarding pipeline, dan platform management. | SuperAdmin specific endpoints (partial) | 🔄 PARTIAL - Frontend ready, SuperAdmin API belum lengkap
FEAT-016 | Chatbot Management System | Bot Management | Not Started | High | Sistem manajemen chatbot lengkap dengan CRUD operations, training, chat interface, dan performance monitoring. | /api/v1/chatbots (semua endpoint TODO) | ❌ NOT STARTED - Semua endpoint TODO
FEAT-017 | Conversation Management System | Communication Management | Not Started | High | Sistem manajemen conversation lengkap dengan message handling, conversation tracking, dan analytics. | /api/v1/conversations (semua endpoint TODO) | ❌ NOT STARTED - Semua endpoint TODO
FEAT-018 | Advanced Analytics Dashboard | Analytics & Reporting | Not Started | Medium | Dashboard analytics advanced dengan real-time metrics, historical data visualization, dan predictive analytics. | /api/v1/analytics (semua endpoint TODO) | ❌ NOT STARTED - Semua endpoint TODO
FEAT-019 | Automation Playbooks | Automation | Not Started | High | Sistem automation playbooks untuk workflow automation, bot responses, dan intelligent routing. | Automation endpoints (belum ada) | ❌ NOT STARTED - Belum ada endpoints
FEAT-020 | Advanced Security Features | Security | Not Started | High | Fitur keamanan advanced termasuk 2FA, audit logging, security compliance, dan threat detection. | Security endpoints (belum ada) | ❌ NOT STARTED - Belum ada endpoints
FEAT-021 | Real-time Notifications | Communication | Not Started | Medium | Sistem notifikasi real-time dengan WebSocket integration, push notifications, dan notification preferences. | WebSocket endpoints (belum ada) | ❌ NOT STARTED - Belum ada endpoints
FEAT-022 | Advanced Integration Hub | Integration | Not Started | Medium | Hub integrasi advanced dengan support untuk lebih banyak platform, API management, dan integration marketplace. | Integration management endpoints (belum ada) | ❌ NOT STARTED - Belum ada endpoints